## Technical
Phase-wise description | Stage | Start Date
Inception Phase : P1 |  |  | Project start date | 2015-01-02
Iteration 1 |  | 2015-01-02 | Total Project weeks | 19 weeks
Identify and outline req | P1I1 |  | Inception Phase | 4 weeks | 2015-01-02
detailed usecase scenarios | P1I1 |  | Elaboration Phase | 6 weeks | 2015-01-03 | 2 weeks buffer before eosp
detailed system wide requirements | P1I1 |  | Construction Phase | 7 weeks | 05-25-2015
Analyse existing system | P1I1 |  | Transition Phase | 2 weeks | 14-27-2015 | 2 weeks buffer BEFOR eosp
Iteration 2 |  | 02-15-2015
Identify and outline req | P1I2
detailed usecase scenarios/ model | P1I2
detailed system wide requirements | P1I2
Conceptualize Architecture | P1I2
Develop prototype* | P1I2
Analyse existing system | P1I2
Elaboration Phase : P2 |  | 2015-01-03
Iteration 1
refine usecase scenarios
refine system wide requirements
Identify and outline requirement
develop architecture
Create test cases - architecture
Iteration 2 |  | 03-15-15
refine usecase scenarios
refine system wide requirements
Identify and outline requirement
develop architecture
Create test cases - architecture / detailed design
Draft Detailed-Design
Iteration 3 |  | 03-29-2015
Finalize architecture
Develop detailed design
Create test case - detailed design
Identify and set up development environment
2 week Buffer- to fix things - EOSP - Party
Construction - Phase 3 |  | 05-25-2015
Iteration 1
Refine req/arch/design
Develop code
write testcases
test code - Unit
verify with req document
Iteration 2
Refine req/arch/design
Develop code
write testcases
test code - unit, integration
verify with req document
Iteration 3
verify with req document
Develop code
write testcases
test code - unit, integration
Iteration 4
verify with req document
Develop code
write testcases
test code - unit, integration
Transition Phase |  | 2015-07-14
Iteration 1
Finalize Product
Prepare for delivery
Prepare for EOSP
Iteration 2
Finalize Product
Deliver Product
Present EOSP